## April 1
|  |  | Weekly Sprint Sheet |  | Team Members | Email
Project: | 5 |  |  |  | Brian Goldenberg | bgolde2@uic.edu
Week Of: | 2019-04-30 |  |  |  | Harsh Gupta | hgupta20@uic.edu
[5 empty] | Emmanuel Utomi | eutomi2@uic.edu
[5 empty] | Kevin Barrett | kbarre8@uic.edu
Action Item | Item ID | Team Member | Last Week | This Week | Next Week | Issues
Working on the basic version of the game and the gui | 1 | All | Still needs to be done | Modified code to work with multiple clients
Trying to Implement the game using sockets and connections, as done in project 4 | 2 | All | Still Working | Works with different clients and allows multiple connections
Each client can see a list of all people currently on the server. And Client GUI | 4 | Harsh | NA | Done with this each client and see how may players are connected
Client can click on buttons with cards on them | 5 | Kevin | NA | Started
Game functionality | 6 |  |  | Started
Server GUI | 7 | Emmanuel |  | Started
Documentation | 8 | Kevin and Emmanuel |  | Started
Instructions on How to play, UML, Activity | 9 | Brian and Harsh
Final Report | 10 | Harsh